## Slide 1: Product Development Process
Daniel Juliano
Director, MSU Technology Transfer Office
2023

## Slide 2: Product Development Process (PDP)
Structured approach to plan and execute the full product life cycle
Distinct Project Phases with Exit Gates ( )
  Each Phase has specific, pre-defined requirements spanning marketing, finance, process, equipment, IP, quality & reliability, supply chain, operations, EHS, etc.
  Exit Gate Reviews conducted with larger group; go/no-go decisions made
Why?
  Improve mutual understanding, communication, & decision making
Ideas and Business Case
Concept & Feasibilty
Development
Pilot Production
Volume Production
PDP details vary by company but principles are similar

## Slide 3: Product Development Process (PDP)
Ideas and Business Case
Concept & Feasibilty
Development
Pilot Production
Volume Production
Uncertainty decreases and cost increases through project
Risk
Cost
Notes: Characteristically, the product development process is messy and uncertain early in the process, and success is a function of having a technically sharp open mind and exploring as many possibilities as quickly as possible while not losing sight of the project goals. Don’t expect every Product Development effort to result in a product reaching volume production. Many should and must be terminated at one of the phase gates, if/when it becomes clear that the product is not going to meet requirements, either for performance, cost, or market window (timing). That is the primary purpose of the phase gates—to end a doomed project early, while time and $ invested in it are still small!

## Slide 4: General Execution Discipline During all project phases
Project plan e.g. in MS Project
  Gantt Chart with milestones
  Budget projection
  Resource allocation
Notes: The 2 biggest problems I have seen with the management of projects are 1) poor alignment, so the people involved aren’t all rowing the boat in the same direction 2) sloppy execution, which can be largely alleviated with a few tools that promote good organization. Everyone should be familiar with the basics of project management, including Gantt Charts, while not being psychologically rigid about expectations for the project plan to be static. Adopt the principles of Agile software development and embrace flexibility. Old school project management was done in MS Project but there are many newer tools for team projects online, some of which are more focused on collaboration and task management than budget and resource allocation.

## Slide 5: General Execution Discipline During all project phases
Project plan e.g. in MS Project
  Gantt Chart with milestones
  Budget projection
  Resource allocation
Action Item tracking e.g. in MS Excel
  Owners assigned with expected & actual completion dates
  Color-coded by status, with history for each item
  Updated live during working meetings (and offline as needed)
Notes: The 2 biggest problems I have seen with the management of projects are 1) poor alignment, so the people involved aren’t all rowing the boat in the same direction 2) sloppy execution, which can be largely alleviated with a few tools that promote good organization.

## Slide 6: General Execution Discipline During all project phases
Project plan e.g. in MS Project
  Gantt Chart with milestones
  Budget projection
  Resource allocation
Action Item tracking e.g. in MS Excel
  Owners assigned with expected & actual completion dates
  Color-coded by status, with history for each item
  Updated live during working meetings (and offline as needed)
Review meetings
  Project owners present latest results, progress against plan, results achieved vs requirements
Notes: Review meetings keep everyone aligned, and harness the power of the hive mind to help the team make optimal decisions and to spot potential risks early. They are also critical for phase exits—both to ensure appropriate decisions are made regarding whether the project should move on to the next phase, and to get buy-in for doing so.

## Slide 7: General Execution Discipline During all project phases
Project plan e.g. in MS Project
  Gantt Chart with milestones
  Budget projection
  Resource allocation
Action Item tracking e.g. in MS Excel
  Owners assigned with expected & actual completion dates
  Color-coded by status, with history for each item
  Updated live during working meetings (and offline as needed)
Review meetings
  Project owners present latest results, progress against plan, results achieved vs requirements
Frequent customer interaction, both formal and informal
  Keep project synchronized with evolving customer needs
Notes: Customer needs can and will change during your NPI project, and the project goals must stay aligned with the customer needs. Further, depending on project progress, you might need to negotiate with the customer e.g. new product specs, product release schedule.

## Slide 8: General Execution Discipline During all project phases
Project plan e.g. in MS Project
  Gantt Chart with milestones
  Budget projection
  Resource allocation
Action Item tracking e.g. in MS Excel
  Owners assigned with expected & actual completion dates
  Color-coded by status, with history for each item
  Updated live during working meetings (and offline as needed)
Review meetings
  Project owners present latest results, progress against plan, results achieved vs requirements
Frequent customer interaction, both formal and informal
  Keep project synchronized with evolving customer needs
Weekly reports by each project member
  Focus on accomplishments & issues rather than mere activities
These key tools ensure alignment and efficient execution
Notes: These tools are basic but the trick is putting them into effective practice.

## Slide 9: Phase 1—Ideas & Business Case Key points
This phase usually owned by Product Marketing function
Driven by market requirements
  Voice of the Customer
  SWOT analysis
Create Marketing Requirements Document (MRD), which drives the Product Requirements Document (PRD)

## Slide 10: Phase 1—Ideas & Business Case Key points
This phase usually owned by Product Marketing function
Driven by market requirements
  Voice of the Customer
  SWOT analysis
Create Marketing Requirements Document (MRD), which drives the Product Requirements Document (PRD)
Project definition (e.g. project charter)
Preliminary business case, pro forma financials
Finalize checklist, budget, and schedule for next stage
Exit criteria depend on company and may be strategic and/or a strictly financial metric (e.g. NPV, ROI)

## Slide 11: Risk Management tools During Phase 1—Ideas and Business Case phase
Sensitivity analysis of business case
  What are the key levers that can affect the financial viability of the project?
Notes: Concurrent with the drive toward new product release, it is appropriate to manage risk through a series of activities that change vs phase.

## Slide 12: Phase 2—Concept and Feasibility Key points
PRD may drive a functional spec for a particular product design or generation
  May include business case
Confirm or modify MRD, PRD
Notes: The C&F exit gate is a critical step in ensuring that the inherently ambiguous nature of the R&D stage does not persist longer than it has to, but also that the project does not proceed to the more expensive stages too early. In the later stages, the product development process is more predictable (time and $) and success is more a function of disciplined execution.

## Slide 13: Phase 2—Concept and Feasibility Key points
PRD may drive a functional spec for a particular product design or generation
  May include business case
Confirm or modify MRD, PRD
Invention/discovery resolved at this phase; solely engineering execution going forward
Finalize checklist, budget, and schedule for next phase
Demonstrate that the idea is likely to work

## Slide 14: Risk Management tools During Phase 2—Concept and Feasibility phase
Sensitivity analysis of business case
  Identify key levers that can affect the financial viability of the project
Fishbone analysis as problem solving tool
  Effective problem solving minimizes technical risk
  Fishbone approach separates brainstorming of potential causes from the evaluation of their likelihood, facilitates success
Notes: Fishbone analysis is a structured problem solving tool that is often used to troubleshoot quality problems. However, it is also effective for engineering problem solving, in phase 2 and beyond.

## Slide 15: Risk Management tools During Phase 2—Concept and Feasibility phase
Sensitivity analysis of business case
  Identify key levers that can affect the financial viability of the project
Fishbone analysis as problem solving tool
  Effective problem solving minimizes technical risk
  Fishbone approach separates brainstorming of potential causes from the evaluation of their likelihood, facilitates success
FMEA
  Anticipate (known) potential issues
  Items scored on impact severity, likelihood of occurrence, and ability to detect
  Associate a test/interlock/control for each item
  Contingency/mitigation plan for each risk if detected

## Slide 16: Phase 3—Development Key points
Manufacturing equipment designed and tested, with robust manufacturing processes
  Intense focus on rooting out of issues in the product design
  ECO release documentation for both equipment and process
  Close analysis of performance, costs, pricing models vs PRD
  Quality checkpoints and metrics identified
Finalize checklist, budget, and schedule for next phase
Create a real product and confirm that it meets requirements

## Slide 17: Risk Management tools During Phase 3—Development phase
Sensitivity analysis of business case
  Identify key levers that can affect the financial viability of the project
Fishbone analysis as problem solving tool
  Effective problem solving minimizes technical risk
  Fishbone approach separates brainstorming of potential causes from the evaluation of their likelihood, facilitates success
FMEA
  Anticipate (known) potential issues and create contingency plans
  Encompass technical, manufacturing, supply chain, quality & reliability, IT, logistics, and business risks
RCCA (Root Cause & Corrective Action)
  Fishbone analysis to identify root cause
  Corrective action to prevent recurrence
Process window checks
  Need robust processes with sufficiently wide window

## Slide 18: Phase 4—Pilot Production Key points
Refinement of manufacturing processes, procedures
  Intense focus on rooting out of bugs in the manufacturing process
  Confirmation of costs, pricing, capacity models
  Initiate SPC data gathering, analysis
Develop robust manufacturing process

## Slide 19: Risk Management tools During Phase 4—Pilot Production phase
Sensitivity analysis of business case
  What are the key levers that can affect the financial viability of the project?
RCCA (Root Cause & Corrective Action)
  Fishbone analysis to identify root cause
  Corrective action to prevent recurrence
FMEA
  Anticipate (known) potential issues and create contingency plans
  Encompass technical, manufacturing, supply chain, quality & reliability, IT, logistics, and business risks
  Used intensively for changes to production processes and equipment
Proto-SPC implementation
  Early look at production statistics

## Slide 20: Phase 5—Volume Production Key points
Product hand off to Manufacturing organization
Ramp production volume
Continuous improvement
  Yield improvement
  Cost reduction
  SPC
Product Development team available to
support escalations when needed